## People
Team
SL. No | Name | Role | E - Mail ID | Contact #
1 | Nitish Kumar | Trainee | nitishk@virtusa.com | 8770277336
2 | Swarna Telugu | Trainee | swarnat@virtusa.com | 7893106271
3 | S.Achyutha Reddy | Trainee | sunketar@virtusa.com | 8686038652
4 | Sura Sai Priya | Trainee | priyasu@virtusa.com | 9553682629
5 | Mukesh Kumar | Trainee | gmukesh@virtusa.com | 8438419892
6 | A.Shailini | Trainee | ashailini@virtusa.com | 9133670705

## Version History
;
Project Information
| Project: | Online Bus Ticket Reservation system for Travel Line
| Client: | VIRTUSA
| Start Date: | 24/06/2019
| Team: | Team-4
| Date | Description | Version | Author | Reviewer
| 24-06-2019 | BRD | 1

## Product Backlog
ONLINE TICKET RESERVATION SYSTEM FOR TRAVEL LINE
Product Backlog
User Story Id | Module | User Stories | Priority | Sprint Details | Status
USID1 | User | User should be able to search for a service.
USID2 | User | User should be able to select a service.
USID3 | User | User should be able to view the schedule.
USID4 | User | User should be able to select any number of seats.
USID5 | User | User should be able to enter the passenger/s details.
USID6 | User | User should be able to view the master passenger details.
USID7 | User | User should be able to view the service details.
USID8 | User | User should be able to retrieve the booked ticket details.
USID9 | User | User should be able to give the feedback.
USID10 | User | User should be able to contact admin.
USID11 | User | User should be able to view the gallery.
USID12 | User | User should be able to cancel the tickets.
USID13 | User | User should be able to pay using credit card.
USID14 | User | User should be able to recover money for cancelled tickets.
USID15 | Admin | Admin should be able to add services.
USID16 | Admin | Admin should be able to view the feedback given by the users.
USID17 | Admin | Admin should be able to modify the services.
USID18 | Admin | Admin should be able to authenticate with valid credentials.
USID19 | Admin | Admin should be able to add new adiministrator

## Sprint TimeLines
Project Timelines
Sprint No | Title | Start Date | End Date | Weeks | Days | Effort - Hrs | Release Date | Review Date | Retrosp Date | Success Criteria | Remarks/Comments
1 | User should be able to search for a service. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
2 | Usershould be able to select a service. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
3 | User should be able to view the schedule. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
4 | User should be able to select any number of seats. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
5 | User should be able to enter the passenger/s details. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
6 | User should be able to view the master passenger details. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
7 | User should be able to view the service details. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
8 | User should be able to retrieve the booked ticket details. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
9 | User should be able to give the feedback. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
10 | User should be able to contact admin. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
11 | User should be able to view the gallery. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
12 | User should be able to cancel the tickets. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
13 | User should be able to pay using credit card. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
14 | User should be able to recover money for cancelled tickets. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
15 | Admin should be able to add services. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
16 | Admin should be able to view the feedback given by the users. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
17 | Admin should be able to modify the services. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
18 | Admin should be able to authenticate with valid credentials. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019
19 | Admin should be able to add new adiministrator. | 24-06-2019 | 15-7-2019 | 0 |  | 3 | 16-07-2019 | 17-07-2019

## Sprint 1 - Plan
Sprint 1 - Plan
Days | Date | Day | 9.00 - 10.00 | 10.00-11.00 | 11.00-12.00 | 12.00-1.00 | 1.00-2.00 | 2.00-3.00 | 3.00-4.00 | 4.00 - 5.00 | 5.00 - 6.00
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16

## Sprint 1 - Effort Estimate
Sprint 1 Effort Estimate
No Of Stories |  | Level - Hours Distribution |  | Hours Available Per Person |  |  | 0 | 0
Level. | Count. | Level. | Total Hrs | Days | Date | Day | Hours Avail | Hours Spt
Simple | 2 | Simple | 223
Medium | 2 | Medium | 0
Complex | 3 | Complex | 0
Grand Total | 7 | Grand Total | 223

## Sprint 1 - Effort Est Details
Sprint 1 -Estimate
Sl No | Story | Assigned To | Level | UX | UI | Design | Code | Unit Testing | Self Review | Integration | Testing | Total in hrs
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Sprint 1 Backlog
Sprint BackLog - Sprint 1
Task Id | UserStory ID | Tasks | Person | Estimated (Hrs) | Status
T1 | USID1 | User should be able to search for a service.
T2 | USID2 | User should be able to select a service.
T3 | USID3 | User should be able to view the schedule.
T4 | USID4 | User should be able to select any number of seats.
T5 | USID5 | User should be able to enter the passenger/s details.
T6 | USID6 | User should be able to view the master passenger details.
T7 | USID7 | User should be able to view the service details.
T8 | USID8 | User should be able to retrieve the booked ticket details.
T9 | USID9 | User should be able to give the feedback.
T10 | USID10 | User should be able to contact admin.
T11 | USID11 | User should be able to view the gallery.
T12 | USID12 | User should be able to cancel the tickets.
T13 | USID13 | User should be able to pay using credit card.
T14 | USID14 | User should be able to recover money for cancelled tickets.
T15 | USID15 | Admin should be able to add services.
T16 | USID16 | Admin should be able to view the feedback given by the users.
T17 | USID17 | Admin should be able to modify the services.
T18 | USID18 | Admin should be able to authenticate with valid credentials.
T19 | USID19 | Admin should be able to add new adiministrator

## Miscalleneous
Project Repository Details |  |  | Configuration Details
SL. No | Name | Location | SL. No | Name | Branch | Location
1 |  |  | 1
2 |  |  | 2
3 |  |  | 3
4 |  |  | 4
5 |  |  | 5
Hardware Checklist
|  |  | SL. No | Name | Category | Remarks
1
2
3
4
5

## Legends
Status | Level